## Sheet1
|  | ANNEX 3 to the Partnership Agreement (prepared: 10.03.2011.) | „The Ancient Cult Sites for Common Identity on the Baltic Sea Coast” - „CULT IDENTITY”
|  | Lead partner | Riga Planning Region, LV
|  | Number of partners | 6
|  | Duration | 1+ 32 months
|  | Implementation period | 02.12.2010.- 31.08.2013.
WP | Responsible partner | Activities | 2010 | 2011 | [11 empty] | 2012 | [11 empty] | 2013
|  |  | Dec | Jan | Feb | March | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | Jun | Jul | Aug
WP1 |  | Project Management | 2010 Dec: MS 1; 2011 Jan: MS 2; 2011 May: MS 3; 2011 Sept: MS 4; 2012 Jan: MS 5; 2012 May: MS 6; 2012 Sept: MS 7; 2013 Jan: MS 8; 2013 May: MS 9
Responsible for WP: Riga Planning Region (RPR) | RPR | 1.1.Kick-off meeting in Riga, LV | 2011 Feb: 17.II. LV
| RPR | 1.2.Project Launch conference, in Riga, LV | 2011 Feb: 18.II. LV
1.3. Project Steering Group meetings (PSG)
| RPR, PP | 1.3.1. Establishment of Project Steering Group | bar: 2011 Jan to 2011 Feb
| RPR, PP | 1.3.2. Development of Roles of Procedure of PSG | bar: 2011 Jan to 2011 Feb
| RPR | 1.3.3. 1st PSG meeting - virtualy | 2011 May: WEB
| GCM, RPR | 1.3.4. 2nd PSG meeting (combined with 1.4.3., 2.5.) in Gavleborg, SE | 2011 Sept: 15.IX SE
| RPR | 1.3.5. 3rd PSG meeting - virtualy | 2012 Jan: WEB
| ZPR, RPR | 1.3.6. 4th PSG meeting (combined with 1.4.5., 2.9.) in Jelgava, LV | bar: 2012 May
| RPR | 1.3.7. 5th PSG meeting - virtualy | 2012 Sept: WEB
| KPR, RPR | 1.3.8. 6th PSG meeting (combined with 1.4.7.) in Kurzeme, LV | bar: 2013 Jan
| RPR | 1.3.9. 7th PSG meeting - virtualy | 2013 May: WEB
| ZPR, RPR | 1.3.10. 8th PSG meeting / Kick-on meeting (combined with 5.9.), in Tērvete, LV | bar: 2013 Aug
1.4. Project Management Team meetings (PMT)
| RPR | 1.4.1. 1st PMT meeting (combined with 1.1.) | 2011 Feb: 17.II.
| HMF, RPR | 1.4.2. 2nd PMT meeting (combined with 2.2.) in Tartu, EE | 2011 May: 27.V EE
| GCM, RPR | 1.4.3. 3rd PMT meeting (combined with 1.3.4.,2.5.) in Gavleborg, SE | 2011 Sept: 14.IX SE
| RPR | 1.4.4.4th PMT meeting (combined with 2.7.) | bar: 2012 Jan
| ZPR, RPR | 1.4.5. 5th PMT meeting (combined with 1.3.6., 2.9.) in Jelgava, LV | bar: 2012 May
| HMF, RPR | 1.4.6. 6th PMT meeting ( combined with 3.2.3.) in Tartu, EE | bar: 2012 Sept
| KPR, RPR | 1.4.7. 7th PMT meeting (combined with 1.3.8.) in Kurzeme, LV | bar: 2013 Jan
| RPR | 1.4.8. 8th PMT meeting, virtualy | 2013 May: WEB
| RPR, PP | 1.5. Establishment of managing and accounting system | bar: 2011 Jan
| PP | 1.5.1. Project management
| PP | 1.5.2. Project financial management
| RPR, PP | 1.5.3. Project Communication activities: preparation of Communication plan; daily comunication: publications on project in partners websites, press releases etc.
| RPR, PP | 1.6. Preparation and coordination of partnership agreements | bar: 2011 Jan to 2011 March
| RPR, PP | 1.7. Preparation of the partner's Progress Report; submittion to the FLC | 2011 May: 15.V.; 2011 Sept: 15.IX.; 2012 Jan: 15.I.; 2012 May: 15.V.; 2012 Sept: 15.IX; 2013 Jan: 15.I.; 2013 May: 15.V
| PP | 1.8. Submittion of approved Partner's Progress Rep.to the LP | 2011 July: 31.VII; 2011 Nov: 30.XI; 2012 March: 31.III; 2012 July: 31.VII; 2012 Nov: 30.XI; 2013 March: 31.III; 2013 Jul: 31.VII
| RPR | 1.8. Preparation and subbmition of the Project Progress Report to JTS | bar: 2011 Aug; 2011 Dec; 2012 Apr; 2012 Aug; 2012 Dec; 2013 Apr
| RPR, PP | 1.9. Preparation and submition of Final report | bar: 2013 Jul to 2013 Aug
WP2 |  | Mapping, analyses amd strategy planning Ancient Cult Places | Dec | Jan | Feb | March | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | Jun | Jul | Aug
Responsible for WP: Hiite Maja Foundation (HMF) | PP | 2.1.Selection of Experts (or project lead specialists as a staff) | bar: Jan to Feb
| HMF | 2.2.Workshop for creation of common principles for exploration, grouping, documentation, mapping, assessment of ancient cult places etc. in the particip.regions, elaboration of assessment criteria (questionnaire); (combined with 1.4.2.) in Tartu, EE | May: 26.V. EE
| PP | 2.3.Exploration of the Objects / selection and summarization of information (historical data about each Object, folklore, rituals, symbols); mapping, photography, survey of Objects in nature | bar: March to Oct
| GCM | 2.4.Research of cult place on the central part of Hög parish *** | bar: May to Aug
| GCM | 2.5.Workshop of experts (combined with 1.3.4., 1.4.3.) in Gavleborg, SE | Sept: 14.,15.IX SE
| PP | 2.6.Assessment of selected Objects (on the base of criteria - for potential application as a tourism product) | bar: Oct to Dec
| VPR | 2.7. Workshop for Analysis of results of WP 2 as well as discussion about common identity of the Baltic Sea region (combined with 1.4.4.), in Valmiera, LV *** | bar: Jan
| HMF, PP | 2.8.Elaboration of the common Development and management Strategy
2.8.1. The team of experts for development of management startegy for ancient Cult sites formed; framework formed | bar: July to Aug
2.8.2. Studies of nat.legislation regarding environm.protection, preservation of the cultural/ historical heritage etc. | bar: Sept to Oct
2.8.3. Development of recommendations for management of Objects | bar: Oct to Dec
2.8.4. Development of specific guidelines in compliance with nat.legislation | bar: Jan to March
2.8.5. Common Development and Management Strategy developed in ENG (information developed in 2.8.1.- 2.8.4. agregated) | bar: Apr
| ZPR, PP | 2.9. Workshop for exchange of experience among partn. in the area of nature protect., preservation of cult./ hist. heritage, management issues etc. (combined with 1.4.5., 1.3.6.) in Jelgava, LV | bar: May
WP3 |  | Development of pilot-routes | Dec | Jan | Feb | March | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | Jun | Jul | Aug
Responsible for WP: Vidzeme Planning Region (VPR) | PP | 3.1.Developm.of reg.pilot-routs in each participating region (including info about extra serv. – accommodation, treatment s., etc.), linking of pilot-rotes; 3 local meetings for pilot-route development organized with local tourism operators | bar: May to Feb
3.2.Internal workshops for exchange of experience
| GCM | 3.2.1. Internal workshop in Gavleborg, SE | bar: LV Jun
| VPR | 3.2.2. Internal workshop in Riga, Vidzeme regions, LV | bar: LV July
| HMF | 3.2.3. Internal workshop (combined with 1.4.6.) in Tartu, EE | bar: LV Sept
| ZPR, KPR | 3.2.4. Internal workshop in Zemgale, Kurzeme regions, LV | bar: LV Aug
3.3.Marking of pilot-routs in the nature (development and installation of info signs, info stands)
| VPR, HMF,GCM | 3.3.1. Development of signs (design) | bar: LV July
| VPR, HMF,GCM | 3.3.2. Development of Informative stands (design) | bar: LV July
| VPR, HMF,GCM | 3.3.3. Coordination of design and instalation of signs with state institutions | bar: LV July to LV Nov
| VPR, HMF,GCM | 3.3.4. Purchase procedure | bar: LV Nov to LV Dec
| PP | 3.3.5. Producing and instalation of signs | bar: LV Jan to LV Apr
WP4 |  | Implementation of the Promotion Activities | Dec | Jan | Feb | March | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | Apr | May | Jun | Jul | Aug
Responsible for WP: Zemgale planning Region (ZPR) / Kurzeme Planning Region (KPR) | RPR | 4.1. Development of Project visual identity - logo, templates, project info stand | bar: Feb to March
4.2.Preparation of Brochure (with pilot-roads, information etc.) | bar: Apr to Aug
| KPR | 4.2.1. Development of design and layout design | bar: Apr to Aug
| KPR | 4.2.2. Traslation LAT to ENG; ENG to LAT | bar: Apr to Aug
| HMF | 4.2.3. Traslation EST to ENG; ENG to EST | bar: Apr to Aug
| GCM | 4.2.4. Traslation Swedish to ENG; ENG to Swedish | bar: Apr to Aug
| KPR | 4.2.5. Printing of broshure; 50 000 copies per country | bar: Apr to Aug
4.3. Development of the Project web-site / virtual museum / maintenance dur.proj.implementation
| RPR | 4.3.1.Developm.of web site, prep.of Project info. In ENG + native languages, digital map | bar: May to Aug
| RPR | 4.3.2. Development of virtual museum, e-museum's content management system | bar: Sept to Dec
| RPR, ZPR | 4.3.3. Processing of materials for virtual museum; preparation of gids' handbook for printing on demand; translation of materials from native languages to ENG | Apr: Demo
4.4. Organization of the introduction tours - preparation works | bar: Aug to Oct
| GCM | 4.4.1. introduction tours for tourism operators / journalists in Gavleborg, SE *** | bar: Sept; Apr
| VPR | 4.4.2. introduction tours for tourism operators / journalists in Riga, Vidzeme regions, LV *** | bar: Sept to Oct; May
| HMF | 4.4.3. Introduction tours for tourism operators / journalists in Tartu, EE *** | bar: Oct; May
| KPR | 4.4.4. Introduction tours for tourism operators / journalists in Kurzeme, Zemgale regions, LV *** | bar: Oct; Jun
| PP | 4.5. Publications on the base of introduction tours *** | bar: Nov to Jun
| ZPR | 4.6. Development of Project presentation materials | bar: July to Aug
4.7. Participation in the tourism fairs – "Balttour","Tur", "Tourest" - organizational issues | bar: Sept to Dec
| ZPR | 4.7.1. Development of design, technical issues | bar: Nov to Dec
| PP | 4.7.2. Participation in the fairs in Göteborg, SE; Riga, LV, Tallin, EE | Jan: EE; Feb: LV; March: SE
| ZPR | 4.9. Festival of Baltic Sea Region Identity as a beginning of new international tradition in Tervete, LV
|  | 4.9.1. Kick-on meeting (combined with 1.3.10.) | Aug: LV, Zemg
|  | 4.9.2. Conference for description of Project results for pot.beneficiaries, discussions about influence of Proj.res.in the implementation of Baltic Sea Strategy | Aug: LV, Zemg
|  | 4.9.3. International culture program, presentation of Project results for potential users – tourists | Aug: LV, Zemg
|  | Project's partners: | Dec: Name; July: E-mail address; Apr: Phones; Oct: Skypenames
|  | Riga Planning Region, Latvia (RPR) | Dec: Liesma Grīnberga; July: liesma.grinberga@rpr.gov.lv; Apr: 371 26462335 / 371 67559823; Oct: liesmagr
|  | Kurzeme Planning Region, Latvia (KPR) | Dec: Zanda Zeidaka; July: zanda.zeidaka@kurzeme.lv; Apr: 371 26310077 / 371 67338738
|  | Vidzeme Planning Region, Latvia (VPR) | Dec: Ineta Puriņa; July: ineta.purina@vidzeme.lv; Apr: 371 64116007 / 371 26382820
|  | Zemgane Planning Region, Latvia (ZPR) | Dec: Linda Šarķe - Fedjajeva; July: linda.sarke@zpr.gov.lv; Apr: 371 63021250 / 371 28807929; Oct: linda.sarke
|  | Count museum of Gävleborg, Sweden (GCM) | Dec: Katarina Eriksson; July: katarina.eriksson@xlm.se; Apr: 46 2665 5618 / 46 7080 03508
|  | Hiite Maja Foundation, Estonia (HMF) | Dec: Ave Anniste; July: ave@hiis.ee; Apr: 37258035358
Other abreviations:
|  | Project partners (PP) | Dec: English (ENG)
|  | First level controle authority (FLC) | Dec: Latvian (LAT)
|  | Project Steering Group (PSG) | Dec: Estonian (EST)
Project Management team (PMT)
Reflected in budget, but not explaned in the WP (***)
Note on C46: User: Activity included in the Application under activity 2.3. without special focus on exscavations.
Note on C49: User: Workshop is not reflected in the AF, only in the budget, BL 7
Note on C78: User: After implementation: Once a year partners make updates of information: checking of information, collection of new information, changes in the web with private loging Lead partner responsible for monitoring of updating
Note on C79: LG: In AF: The period of implemetation is shorter; beginning in the MS 3
Note on T81: User: Demo version should be tested